EcoConnect Global Ltd.

Executive Summary

Transparent, data-driven marketplace infrastructure for verified carbon credits

Grant Application Support Document

Prepared: May 19, 2026

Draft status: grant-ready structure with explicit placeholders. Final submission requires applicant verification, legal review, program-specific eligibility review, and replacement of all missing data.

# Executive Summary

EcoConnect Global Ltd. proposes a 24-month grant-funded pilot to develop transparent, data-driven marketplace infrastructure for verified carbon credits. The project will help SMEs and other organizations identify credible credits, compare project documentation, understand integrity risks, track purchases/retirements, and generate auditable reports. The public-interest case is not simply that carbon markets are large; it is that carbon market participation remains difficult to trust, expensive to navigate, and inaccessible to many smaller buyers.

Recommended funding request: $5,000,000 in government grant funding with a placeholder $1,250,000 applicant match, for a total Phase 1 project budget of $6,250,000. This replaces the source documents' $50,000,000 equity-investment request for grant purposes.

## Why the Project Is Needed

Carbon credit information is fragmented across registries, project documents, broker materials, ratings, and voluntary standards.

Buyers face integrity concerns around additionality, permanence, double counting, safeguards, and claims.

SMEs often lack resources for high-quality diligence and sustainability reporting support.

Project developers need better channels to credible buyers and more transparent documentation workflows.

Government support can de-risk a public-benefit transparency layer that private capital alone may underfund.

## Project Outputs

| Output | Target by Month 24 |
| --- | --- |
| Standardized carbon project profiles | 150 profiles integrated and quality-checked |
| Pilot buyers | 10-20 buyers onboarded |
| Project developers | 5-10 developers onboarded |
| Buyer reports | 50 auditable reports generated |
| Workshops/webinars | 8 public or stakeholder learning sessions |
| Independent evaluation | Final evaluation and scale-readiness report |

## Funding and Financial Sustainability

| Category | Grant Funds | Applicant Match | Total |
| --- | --- | --- | --- |
| Product & Engineering | $1,250,000 | $325,000 | $1,575,000 |
| Data & Verification | $1,000,000 | $225,000 | $1,225,000 |
| Compliance & Governance | $600,000 | $150,000 | $750,000 |
| Pilot Implementation | $750,000 | $225,000 | $975,000 |
| Operations & Staffing | $850,000 | $200,000 | $1,050,000 |
| Outreach & Dissemination | $325,000 | $75,000 | $400,000 |
| Monitoring & Evaluation | $175,000 | $50,000 | $225,000 |
| Contingency | $50,000 | $0 | $50,000 |
| TOTAL | $5,000,000 | $1,250,000 | $6,250,000 |

Long-term revenue will come from subscriptions, API/reporting services, due diligence support, and transaction fees where legally permissible. The base-case forecast reaches positive EBITDA in Year 5, but this depends on validated customer adoption, legal clearance, and partner commitments.

## Grant Readiness Score

Final grant readiness score after this restructuring: 62/100. Original source package score: 34/100. The largest remaining blockers are applicant eligibility, legal/regulatory review, partner LOIs, match evidence, and documented market validation.

## Source Notes

Source documents reviewed:

retirement_idea.docx - concept plan for a global marketplace for carbon credits and sustainability initiatives

retirement_plan.docx - comprehensive business plan for EcoConnect Global Ltd.

retirement_funds_request.docx - detailed $50 million investor-oriented use of funds

External market and compliance sources used for sanity-checking and grant framing:

World Bank - State and Trends of Carbon Pricing: https://www.worldbank.org/en/publication/state-and-trends-of-carbon-pricing

Ecosystem Marketplace - 2024 State of the Voluntary Carbon Market / market contraction article: https://www.ecosystemmarketplace.com/articles/report-the-voluntary-carbon-market-contracted-in-2023-driven-by-drop-off-in-transactions-for-redd-and-renewable-energy/

ICVCM - Core Carbon Principles and Assessment Framework: https://icvcm.org/wp-content/uploads/2024/02/CCP-Book-V1.1-FINAL-LowRes-15May24.pdf

VCMI - Claims Code of Practice and MRA framework: https://vcmintegrity.org/vcmi-claims-code-of-practice/

U.S. Treasury - Voluntary Carbon Markets Joint Policy Statement and Principles: https://home.treasury.gov/system/files/136/VCM-Joint-Policy-Statement-and-Principles.pdf

European Commission - Corporate sustainability reporting / CSRD: https://finance.ec.europa.eu/financial-markets/company-reporting-and-auditing/company-reporting/corporate-sustainability-reporting_en

European Commission - EU Emissions Trading System: https://climate.ec.europa.eu/eu-action/carbon-markets/eu-emissions-trading-system-eu-ets_en

GOV.UK - Environmental reporting guidelines including SECR: https://www.gov.uk/government/publications/environmental-reporting-guidelines-including-mandatory-greenhouse-gas-emissions-reporting-guidance