EcoConnect Global Ltd.

Grant Application Narrative

Transparent, data-driven marketplace infrastructure for verified carbon credits

Grant Application Support Document

Prepared: May 19, 2026

Draft status: grant-ready structure with explicit placeholders. Final submission requires applicant verification, legal review, program-specific eligibility review, and replacement of all missing data.

# 1. Project Title

EcoConnect Global: Transparent Carbon Credit Marketplace and Reporting Infrastructure Pilot

# 2. Applicant and Eligibility

Applicant: EcoConnect Global Ltd. Legal status, incorporation evidence, registration number, tax/VAT ID, bank account, beneficial ownership, and eligible applicant jurisdiction are currently missing and must be confirmed before submission. This narrative assumes the applicant is eligible to receive public funding under the selected grant program.

# 3. Statement of Need

Carbon markets are important tools for climate finance, but the voluntary carbon market has faced a trust and usability crisis. Buyers often cannot easily compare project documentation, integrity risks, price, retirement status, and claims implications. SMEs face a disproportionate burden because they lack internal carbon-market specialists and may not be able to pay for expensive consulting engagements. Project developers also need more transparent access to qualified buyers.

# 4. Project Objectives

Develop a secure MVP that standardizes carbon project information and exposes key diligence signals.

Create an integrity-screening framework aligned with leading market principles and claims guidance.

Pilot the platform with 10-20 buyer organizations and 5-10 project developers.

Generate auditable buyer reports and public learning outputs that reduce information asymmetry.

Complete an independent evaluation and scale-readiness plan by Month 24.

# 5. Project Design and Activities

| Phase | Months | Major Activities | Key Deliverables |
| --- | --- | --- | --- |
| 1. Award mobilization and governance | 1-2 | Finalize grant agreement, appoint project manager, confirm controls, procurement plan, and reporting calendar. | Kickoff pack, governance charter, procurement/compliance file, risk register. |
| 2. Technical discovery and architecture | 1-3 | Validate user requirements, map registries/data sources, define MVP scope, complete security architecture. | Product requirements, architecture diagram, data map, DPIA scope. |
| 3. MVP and data pipeline build | 3-8 | Develop marketplace browser, registry ingestion, standardized project profiles, dashboards, and audit logs. | MVP demo, data pipeline, initial project profiles, QA report. |
| 4. Integrity framework and compliance review | 4-10 | Develop credit quality criteria, claims policy, verification workflow, legal review, and cybersecurity controls. | Integrity methodology, claims policy, legal memo, security test plan. |
| 5. Pilot onboarding | 7-14 | Recruit pilot buyers and project developers, run training, collect feedback, revise UX and reporting outputs. | 10-20 buyer LOIs/users, 5-10 project developer participants, training materials. |
| 6. Transaction and retirement tracking pilot | 12-20 | Test purchase/retirement tracking workflow, reporting, customer support, and public benefit metrics. | Pilot transaction/retirement reports, user satisfaction data, issue log. |
| 7. Public beta and dissemination | 18-22 | Release beta features, publish public learning, hold workshops, prepare scale plan. | Public beta, workshops, methodology note, dissemination report. |
| 8. Evaluation and sustainability planning | 21-24 | Independent evaluation, final reporting, financial sustainability plan, next-stage funding strategy. | Final evaluation, final grant report, commercialization/scale plan. |

# 6. Innovation and Public Benefit

The project combines marketplace usability, standardized registry data, documentation workflows, and reporting tools. The innovation is not a speculative claim that technology alone solves carbon market integrity. The innovation is a structured, auditable workflow that helps non-specialist buyers compare evidence, understand risks, and make more credible purchasing and reporting decisions. Public benefit will be delivered through SME access, transparency outputs, education, and independent evaluation.

# 7. Target Beneficiaries

SMEs and tech-forward companies seeking credible, auditable carbon credit purchasing workflows.

Sustainability project developers that need a transparent channel to qualified buyers.

Public bodies and NGOs interested in market transparency and integrity learning.

Employees and contractors engaged in climate-tech, data engineering, compliance, and impact evaluation roles.

# 8. Expected Outputs and Outcomes

| Objective | Indicator | Baseline | Year 1 Target | Year 2 Target | Data Source | Frequency |
| --- | --- | --- | --- | --- | --- | --- |
| Increase transparency of carbon credit information | Standardized project profiles published in platform | 0 | 50 | 150 | Platform records and data QA logs | Monthly |
| Improve SME access to credible credits | Pilot buyers onboarded | 0 | 5-8 | 10-20 | Signed pilot agreements, CRM | Monthly |
| Support project developer access to buyers | Project developers onboarded | 0 | 3-5 | 5-10 | Onboarding records | Quarterly |
| Strengthen credit integrity screening | Credits/projects screened using documented criteria | 0 | 50 projects | 150 projects | Scoring logs and methodology review | Monthly |
| Enable auditable reporting | Buyer reports generated with audit trail | 0 | 10 | 50 | Platform logs and report samples | Quarterly |
| Build public learning | Workshops/webinars delivered | 0 | 3 | 8 | Event records, attendance logs | Quarterly |
| Measure adoption and user value | Average pilot user satisfaction score | No baseline | >= 75% | >= 80% | User surveys | Quarterly |
| Protect data and security | Critical security incidents | 0 | 0 | 0 | Incident log | Monthly |
| Ensure grant accountability | Reports submitted on time | 0 | 100% | 100% | Grant reporting calendar | Quarterly |
| Avoid overclaiming climate impact | Emissions impact claims verified before publication | 0 | 100% | 100% | Claims review log | Per claim |

# 9. Budget Narrative

The total Phase 1 project budget is $6,250,000, consisting of a $5,000,000 grant request and $1,250,000 placeholder applicant match. Detailed cost lines are provided in Budget Breakdown.xlsx. Grant funds will support product engineering, data infrastructure, verification methodology, legal and compliance review, pilot implementation, operations, stakeholder outreach, monitoring and evaluation, and eligible contingency.

| Category | Grant Funds | Applicant Match | Total |
| --- | --- | --- | --- |
| Product & Engineering | $1,250,000 | $325,000 | $1,575,000 |
| Data & Verification | $1,000,000 | $225,000 | $1,225,000 |
| Compliance & Governance | $600,000 | $150,000 | $750,000 |
| Pilot Implementation | $750,000 | $225,000 | $975,000 |
| Operations & Staffing | $850,000 | $200,000 | $1,050,000 |
| Outreach & Dissemination | $325,000 | $75,000 | $400,000 |
| Monitoring & Evaluation | $175,000 | $50,000 | $225,000 |
| Contingency | $50,000 | $0 | $50,000 |
| TOTAL | $5,000,000 | $1,250,000 | $6,250,000 |

# 10. Organizational Capacity

The source documents describe planned executive roles but do not provide confirmed personnel or resumes. Before submission, the applicant must add named staff, time commitments, advisors, partner roles, and an independent evaluator. Capacity should be demonstrated through technical delivery experience, data engineering capability, compliance support, financial controls, and pilot partner commitments.

# 11. Sustainability After Grant Funding

After the pilot, the platform will seek sustainability through subscriptions, API/reporting services, due diligence support, and legally compliant transaction fees. The grant will de-risk the public-benefit validation phase and create evidence needed for responsible scale-up. Future equity or debt financing should be pursued only after pilot validation and should not be presented as a government grant objective.

# 12. Risk Management

| Risk | Likelihood | Impact | Mitigation | Residual Risk |
| --- | --- | --- | --- | --- |
| Applicant eligibility not confirmed | High | High | Confirm legal entity, jurisdiction, and grant program requirements before submission. | Medium |
| Carbon credit integrity concerns | High | High | Use ICVCM/VCMI-aligned criteria, independent expert review, transparent methodology, and conservative claims. | Medium |
| Regulatory/licensing exposure | Medium | High | Obtain legal opinion on trading, brokerage, payments, AML/KYC, sanctions, and escrow structures. | Medium |
| Overstated financial projections | High | High | Use conservative base case; treat original $120M-$155M Year 5 case as unvalidated upside. | Medium |
| No confirmed pilot customers | High | High | Secure LOIs and define pilot recruitment milestones before submission. | Medium |
| Data rights and quality gaps | Medium | High | Document data sources, licenses, registry terms, quality checks, and audit trails. | Medium |
| Cybersecurity/privacy breach | Medium | High | Implement DPIA, encryption, access controls, penetration testing, incident response, and vendor due diligence. | Medium |
| Grant compliance failure | Medium | High | Set up procurement policy, timesheets, segregation of duties, document retention, and audit trail. | Low-Medium |

# 13. Compliance Statement

The applicant will establish procurement, conflict-of-interest, timesheet, cost allocation, anti-lobbying, data protection, cybersecurity, AML/KYC screening, sanctions screening, claims review, and document retention procedures before incurring grant-funded costs. A legal review is required before any transaction facilitation or claims language is used.

## Source Notes

Source documents reviewed:

retirement_idea.docx - concept plan for a global marketplace for carbon credits and sustainability initiatives

retirement_plan.docx - comprehensive business plan for EcoConnect Global Ltd.

retirement_funds_request.docx - detailed $50 million investor-oriented use of funds

External market and compliance sources used for sanity-checking and grant framing:

World Bank - State and Trends of Carbon Pricing: https://www.worldbank.org/en/publication/state-and-trends-of-carbon-pricing

Ecosystem Marketplace - 2024 State of the Voluntary Carbon Market / market contraction article: https://www.ecosystemmarketplace.com/articles/report-the-voluntary-carbon-market-contracted-in-2023-driven-by-drop-off-in-transactions-for-redd-and-renewable-energy/

ICVCM - Core Carbon Principles and Assessment Framework: https://icvcm.org/wp-content/uploads/2024/02/CCP-Book-V1.1-FINAL-LowRes-15May24.pdf

VCMI - Claims Code of Practice and MRA framework: https://vcmintegrity.org/vcmi-claims-code-of-practice/

U.S. Treasury - Voluntary Carbon Markets Joint Policy Statement and Principles: https://home.treasury.gov/system/files/136/VCM-Joint-Policy-Statement-and-Principles.pdf

European Commission - Corporate sustainability reporting / CSRD: https://finance.ec.europa.eu/financial-markets/company-reporting-and-auditing/company-reporting/corporate-sustainability-reporting_en

European Commission - EU Emissions Trading System: https://climate.ec.europa.eu/eu-action/carbon-markets/eu-emissions-trading-system-eu-ets_en

GOV.UK - Environmental reporting guidelines including SECR: https://www.gov.uk/government/publications/environmental-reporting-guidelines-including-mandatory-greenhouse-gas-emissions-reporting-guidance