EcoConnect Global Ltd.

Implementation Timeline

Transparent, data-driven marketplace infrastructure for verified carbon credits

Grant Application Support Document

Prepared: May 19, 2026

Draft status: grant-ready structure with explicit placeholders. Final submission requires applicant verification, legal review, program-specific eligibility review, and replacement of all missing data.

# Implementation Timeline

This timeline assumes a 24-month grant-funded pilot beginning July 2026. Dates must be revised after award notification and contracting.

| Phase | Months | Major Activities | Key Deliverables |
| --- | --- | --- | --- |
| 1. Award mobilization and governance | 1-2 | Finalize grant agreement, appoint project manager, confirm controls, procurement plan, and reporting calendar. | Kickoff pack, governance charter, procurement/compliance file, risk register. |
| 2. Technical discovery and architecture | 1-3 | Validate user requirements, map registries/data sources, define MVP scope, complete security architecture. | Product requirements, architecture diagram, data map, DPIA scope. |
| 3. MVP and data pipeline build | 3-8 | Develop marketplace browser, registry ingestion, standardized project profiles, dashboards, and audit logs. | MVP demo, data pipeline, initial project profiles, QA report. |
| 4. Integrity framework and compliance review | 4-10 | Develop credit quality criteria, claims policy, verification workflow, legal review, and cybersecurity controls. | Integrity methodology, claims policy, legal memo, security test plan. |
| 5. Pilot onboarding | 7-14 | Recruit pilot buyers and project developers, run training, collect feedback, revise UX and reporting outputs. | 10-20 buyer LOIs/users, 5-10 project developer participants, training materials. |
| 6. Transaction and retirement tracking pilot | 12-20 | Test purchase/retirement tracking workflow, reporting, customer support, and public benefit metrics. | Pilot transaction/retirement reports, user satisfaction data, issue log. |
| 7. Public beta and dissemination | 18-22 | Release beta features, publish public learning, hold workshops, prepare scale plan. | Public beta, workshops, methodology note, dissemination report. |
| 8. Evaluation and sustainability planning | 21-24 | Independent evaluation, final reporting, financial sustainability plan, next-stage funding strategy. | Final evaluation, final grant report, commercialization/scale plan. |

## Milestone Approval Gates

| Gate | Approval Criteria | Decision |
| --- | --- | --- |
| Gate 1 - Mobilization | Grant agreement executed, financial controls active, procurement policy approved, risk register opened. | Proceed to build. |
| Gate 2 - MVP readiness | MVP demo complete, data sources documented, security baseline complete, compliance framework drafted. | Proceed to pilot onboarding. |
| Gate 3 - Pilot operations | LOIs signed, user training complete, support process live, reporting templates tested. | Proceed to transaction/retirement tracking pilot. |
| Gate 4 - Public beta | Independent interim review complete, critical security issues resolved, claims policy approved. | Proceed to dissemination and scale planning. |
| Gate 5 - Closeout | Final evaluation complete, financial report submitted, sustainability plan approved. | Close grant and launch next-stage financing. |