EcoConnect Global Ltd.

Monitoring & Evaluation Plan

Transparent, data-driven marketplace infrastructure for verified carbon credits

Grant Application Support Document

Prepared: May 19, 2026

Draft status: grant-ready structure with explicit placeholders. Final submission requires applicant verification, legal review, program-specific eligibility review, and replacement of all missing data.

# Monitoring and Evaluation Plan

The M&E plan focuses on measurable outputs, adoption outcomes, integrity safeguards, and grant accountability. Baselines are currently zero because the source documents do not provide evidence of existing users, transactions, or verified retirements.

| Objective | Indicator | Baseline | Year 1 Target | Year 2 Target | Data Source | Frequency |
| --- | --- | --- | --- | --- | --- | --- |
| Increase transparency of carbon credit information | Standardized project profiles published in platform | 0 | 50 | 150 | Platform records and data QA logs | Monthly |
| Improve SME access to credible credits | Pilot buyers onboarded | 0 | 5-8 | 10-20 | Signed pilot agreements, CRM | Monthly |
| Support project developer access to buyers | Project developers onboarded | 0 | 3-5 | 5-10 | Onboarding records | Quarterly |
| Strengthen credit integrity screening | Credits/projects screened using documented criteria | 0 | 50 projects | 150 projects | Scoring logs and methodology review | Monthly |
| Enable auditable reporting | Buyer reports generated with audit trail | 0 | 10 | 50 | Platform logs and report samples | Quarterly |
| Build public learning | Workshops/webinars delivered | 0 | 3 | 8 | Event records, attendance logs | Quarterly |
| Measure adoption and user value | Average pilot user satisfaction score | No baseline | >= 75% | >= 80% | User surveys | Quarterly |
| Protect data and security | Critical security incidents | 0 | 0 | 0 | Incident log | Monthly |
| Ensure grant accountability | Reports submitted on time | 0 | 100% | 100% | Grant reporting calendar | Quarterly |
| Avoid overclaiming climate impact | Emissions impact claims verified before publication | 0 | 100% | 100% | Claims review log | Per claim |

## Evaluation Method

Baseline: confirm current platform status, data sources, partners, users, and operational controls at project start.

Monthly monitoring: track outputs, budget burn, risk register, data quality, security issues, and pilot activity.

Quarterly review: assess user adoption, satisfaction, partner progress, grant compliance, and corrective actions.

Mid-term review: independent or semi-independent review at Month 12 to decide whether to proceed to transaction/retirement tracking pilot.

Final evaluation: independent evaluator assesses relevance, effectiveness, efficiency, sustainability, integrity safeguards, and lessons learned.

## Claims and Impact Controls

All impact claims will be reviewed against a claims policy before publication. The platform will separate information services from official certification and will not claim accreditation unless documented. Environmental impact metrics will distinguish between analysis, purchase, and retirement.

## Source Notes

Source documents reviewed:

retirement_idea.docx - concept plan for a global marketplace for carbon credits and sustainability initiatives

retirement_plan.docx - comprehensive business plan for EcoConnect Global Ltd.

retirement_funds_request.docx - detailed $50 million investor-oriented use of funds

External market and compliance sources used for sanity-checking and grant framing:

World Bank - State and Trends of Carbon Pricing: https://www.worldbank.org/en/publication/state-and-trends-of-carbon-pricing

Ecosystem Marketplace - 2024 State of the Voluntary Carbon Market / market contraction article: https://www.ecosystemmarketplace.com/articles/report-the-voluntary-carbon-market-contracted-in-2023-driven-by-drop-off-in-transactions-for-redd-and-renewable-energy/

ICVCM - Core Carbon Principles and Assessment Framework: https://icvcm.org/wp-content/uploads/2024/02/CCP-Book-V1.1-FINAL-LowRes-15May24.pdf

VCMI - Claims Code of Practice and MRA framework: https://vcmintegrity.org/vcmi-claims-code-of-practice/

U.S. Treasury - Voluntary Carbon Markets Joint Policy Statement and Principles: https://home.treasury.gov/system/files/136/VCM-Joint-Policy-Statement-and-Principles.pdf

European Commission - Corporate sustainability reporting / CSRD: https://finance.ec.europa.eu/financial-markets/company-reporting-and-auditing/company-reporting/corporate-sustainability-reporting_en

European Commission - EU Emissions Trading System: https://climate.ec.europa.eu/eu-action/carbon-markets/eu-emissions-trading-system-eu-ets_en

GOV.UK - Environmental reporting guidelines including SECR: https://www.gov.uk/government/publications/environmental-reporting-guidelines-including-mandatory-greenhouse-gas-emissions-reporting-guidance